## Bug Report
Bug ID | Screen Name | Bug Title | Bug Description | Steps to Reproduce | Expected Result | Actual Result | Severity
BR-001 | Home Page → Recently Listed | Car details not displayed, script shown | Car details are not displayed properly and script/animated car appear. | Open app → Home Page → Recently Listed → Select any car | Car details should display correctly | Script/animated shown instead of details | High
BR-002 | Home Page → Recently Listed | Share and Like options not working | User cannot share or like selected car. | Home Page → Recently Listed → Select car → Click Share/Like | User should share/like the car | Share/Like not working | Medium
BR-003 | Home Page → Recently Listed | Call Now feature not working | Call is not initiated on clicking Call Now. | Home Page → Recently Listed → Select car → Call Now | Call should initiate | Call not initiated | High
BR-004 | Near Cars | Original car images not displayed | Original car images are missing. | Open Near Cars screen | Original images should display | Images missing | Medium
BR-005 | Near Cars | Share, Like, Call options not working | Share, Like, and Call options are non-functional. | Near Cars → Select car → Try Share/Like/Call | All options should work | Options not working | High
BR-006 | Near Cars → Dealer Section | Feedback option not available | Feedback option missing in Dealer section. | Near Cars → Select car → Dealer section | Feedback option should be available | Option not available | Medium
BR-007 | Profile | Terms & Conditions and Privacy Policy not opening | Options are disabled and show no content. | Profile → Click T&C / Privacy Policy | Content should display | No content shown | Medium
BR-008 | Profile | Logout functionality not working | User cannot log out from app. | Profile → Click Logout | User should log out | Logout not working | High
BR-009 | Overall Application | Application performance is slow | App takes time to load features. | Open app → Navigate screens | Fast response | Slow loading | Medium
BR-010 | Overall Application | UI not clear, car images missing | UI unclear and car images not visible. | Open app → Browse car listings | Clear UI with images | Images missing, unclear UI | Medium